## Read Me
S/4HANA Master Data Readiness Scorecard
Companion to the Taksh Solutions article “Master Data Readiness: The Dependencies That Make or Break an S/4HANA Go-Live”
https://takshsolutions.com/s4hana-master-data-dependencies/
Tab | What it is for
Dependency Map | The manufacturing master data objects in load order, with what each depends on, its owner and load status. A row is flagged if it is loaded before a predecessor.
Validation Rules | Object-level and cross-object rules with records checked and failures; pass rate and pass/fail calculate against each rule's threshold.
Readiness Scorecard | Completeness, accuracy, cross-object checks and business sign-off per object and plant, rolled up to a Ready / At risk / Not ready status and an overall readiness percentage.
Mock Load Trend | Readiness % for each object across mock loads, so you can see whether quality is improving fast enough for the cutover date.
How to use | 1) Confirm the object list and dependencies for your landscape. 2) Agree rules and thresholds with data owners. 3) Update after every mock load. 4) Use the scorecard as evidence in the go/no-go decision.
Legend | Yellow fill = input cell. White cell = formula (do not overwrite). Drop-down lists are provided where options are fixed.
Please note | A generic starting template, not a substitute for a programme-specific assessment. Adapt criteria, weights and thresholds to your landscape and governance. Provided as-is by Taksh Solutions LLC.
Need help? | Contact Taksh Solutions — info@takshsolutions.com · +1 208 918 1022 · takshsolutions.com/contact

## Dependency Map
Dependency Map
Load in sequence. 'Sequence check' flags any object marked Loaded while a predecessor is not.
Yellow cells are inputs. White cells are formulas — don't overwrite them.
Seq | Object | Depends on (Seq) | Owner | Load status | Sequence check | Notes
1 | Organisational structure (plants, storage locations, MRP areas) |  |  | Not started
2 | Business partners (suppliers, customers) | 1 |  | Not started
3 | Material master — basic data | 1 |  | Not started
4 | Material master — plant / MRP views | 3 |  | Not started
5 | Bills of material | 4 |  | Not started
6 | Work centres / resources | 1 |  | Not started
7 | Routings | 4,6 |  | Not started
8 | Production versions | 5,7 |  | Not started
9 | Planning data / PDS (if PP/DS) | 8 |  | Not started
10 | Purchasing info records, contracts, source lists | 2,4 |  | Not started
11 | Stock balances | 4 |  | Not started
12 | Open purchase / production / sales orders | 8,10,11 |  | Not started

## Validation Rules
Validation Rules
Pass rate = 1 − failures ÷ records checked. Result is Pass when pass rate meets the threshold.
Yellow cells are inputs. White cells are formulas — don't overwrite them.
Rule ID | Object | Rule type | Rule | Records checked | Failures | Pass rate | Threshold | Result | Owner | Notes
R01 | Material master | Object-level | MRP type, lot size and procurement type populated for every plant material | 12480 | 37 | 99.7% | 99% | Pass |  | Example figures — replace with your mock load results
R02 | Material master | Object-level | Base unit of measure consistent with BOM and routing usage |  |  |  | 99%
R03 | Bills of material | Cross-object | Every BOM component exists as a material in the same plant |  |  |  | 99%
R04 | Work centres | Object-level | Capacity, formulas and cost centre assigned |  |  |  | 99%
R05 | Routings | Cross-object | Every operation references an active work centre |  |  |  | 99%
R06 | Routings | Object-level | Standard values present and plausible (no zero or extreme times) |  |  |  | 99%
R07 | Production versions | Cross-object | Each version references a released BOM and routing with valid dates |  |  |  | 99%
R08 | Sources of supply | Cross-object | Every purchased material has a valid source of supply |  |  |  | 99%
R09 | Stock balances | Reconciliation | Quantity and value agree with legacy within tolerance |  |  |  | 100%
|  |  | Rules passing | 1 of 1

## Readiness Scorecard
Readiness Scorecard | [9 empty] | Target | 98%
Ready when completeness, accuracy and cross-object checks all meet target and the business owner has signed off. | [9 empty] | At-risk floor | 90%
Yellow cells are inputs. White cells are formulas — don't overwrite them.
Object | Plant | Completeness % | Accuracy % | Cross-object checks % | Business sign-off | Lowest score | Status | Data owner | Notes
Material master | 1000 | 99.5% | 97% | 99% | No | 97% | At risk |  | Example figures — replace with your results
Bills of material | 1000 |  |  |  | No
Work centres / resources | 1000 |  |  |  | No
Routings | 1000 |  |  |  | No
Production versions | 1000 |  |  |  | No
Planning data / PDS | 1000 |  |  |  | No
Sources of supply | 1000 |  |  |  | No
Stock balances | 1000 |  |  |  | No
Open orders | 1000 |  |  |  | No
Objects assessed |  | 1
Ready |  | 0
At risk |  | 1
Not ready |  | 0
Overall readiness |  | 0%

## Mock Load Trend
Mock Load Trend
Enter the lowest score (or readiness %) per object after each mock. Trend compares the latest mock with the first.
Yellow cells are inputs. White cells are formulas — don't overwrite them.
Object | Mock 1 | Mock 2 | Mock 3 | Dress rehearsal | Latest | Change since Mock 1 | On track for target?
Material master | 86% | 93% | 97% |  | 97% | 11% | Watch
Bills of material
Work centres / resources
Routings
Production versions
Planning data / PDS
Sources of supply
Stock balances
Open orders