## Read Me
SAP S/4HANA Production Planning — Cutover Template Pack
Companion to the Taksh Solutions article “A Practical Cutover Checklist for Production Planning in SAP S/4HANA”
https://takshsolutions.com/s4hana-production-planning-cutover-checklist/
Tab | What it is for
Cutover Runbook | Every cutover task with phase, owner, predecessor, planned timing and a verification step. Planned end times calculate automatically. Use one copy per mock cutover and compare actual against planned durations.
Open Order Strategy | Decide, object by object, whether open orders and documents are migrated, closed in the legacy system, or regenerated by planning in S/4HANA — and track counts against the decision.
Load & Reconciliation | Master and transactional data loaded in dependency order, with legacy vs. S/4HANA counts and values, variance, tolerance check and business sign-off.
Go-No-Go | The criteria agreed in advance for the go-live decision. The overall result calculates from the individual criteria.
Hypercare Log | Issues raised after go-live with priority, owner, status and days open, so the team can see whether stability is improving.
How to use | 1) Replace the example rows with your own plants, objects and owners. 2) Agree the Go-No-Go criteria before the first mock cutover. 3) Re-baseline the runbook after each mock using the actual durations. 4) Keep this file in a shared location with version control.
Legend | Yellow fill = input cell. White cell = formula (do not overwrite). Drop-down lists are provided for Phase, Status, Strategy, Met? and Priority.
Please note | These are generic starting templates, not a substitute for a programme-specific cutover plan. Adapt tasks, objects and tolerances to your system landscape, data volumes and governance. Provided as-is by Taksh Solutions LLC.
Need help? | Contact Taksh Solutions — info@takshsolutions.com · +1 208 918 1022 · takshsolutions.com/contact

## Cutover Runbook
Cutover Runbook
One row per task. Planned End = Planned Start + Duration. Variance compares actual vs planned duration.
Yellow cells are inputs. White cells with black text are formulas — don't overwrite them.
ID | Phase | Task | Workstream | Owner | Predecessor (ID) | Planned Start | Duration (hrs) | Planned End | Actual Start | Actual End | Actual Duration (hrs) | Variance (hrs) | Status | Verification / evidence | Notes
T01 | Pre-cutover | Confirm go/no-go for cutover start | PMO | Cutover lead |  | 2026-11-06 18:00 | 1 | 2026-11-06 19:00 |  |  |  |  | Not started | Go decision recorded in Go-No-Go tab | Example start time — replace with your cutover start
T02 | Pre-cutover | Freeze master data changes in legacy (emergency process only) | Master data | MD lead | T01 |  | 0.5 | [5 empty] | Not started | Freeze notice issued; change log closed
T03 | Pre-cutover | Close / complete agreed legacy production orders | Production | Production planner | T02 |  | 4 | [5 empty] | Not started | Open order count matches Open Order Strategy
T04 | Legacy shutdown | Stop legacy planning and execution transactions | Basis / PMO | Cutover lead | T03 |  | 0.5 | [5 empty] | Not started | User access locked; batch jobs suspended
T05 | Legacy shutdown | Take final legacy extracts (stock, open orders, master data deltas) | Data migration | Data lead | T04 |  | 3 | [5 empty] | Not started | Extract record counts logged in Load & Reconciliation
T06 | Load | Load material master (plant views, MRP data) | Data migration | Data lead | T05 |  | 4 | [5 empty] | Not started | Count and spot-check vs legacy
T07 | Load | Load bills of material | Data migration | Data lead | T06 |  | 3 | [5 empty] | Not started | All components exist in plant; counts reconcile
T08 | Load | Load work centres / resources | Data migration | Data lead | T06 |  | 2 | [5 empty] | Not started | Capacities and formulas validated
T09 | Load | Load routings | Data migration | Data lead | T08 |  | 3 | [5 empty] | Not started | Every operation references an active work centre
T10 | Load | Create production versions | Data migration | PP lead | T07,T09 |  | 2 | [5 empty] | Not started | Every version references released BOM and routing
T11 | Load | Load sources of supply (info records, scheduling agreements, source lists) | Procurement | Procurement lead | T06 |  | 2 | [5 empty] | Not started | Counts reconcile
T12 | Planning setup | Transfer planning master data / generate PDS (if embedded PP/DS is used) | PP/DS | PP lead | T10 |  | 2 | [5 empty] | Not started | Expected products and resources present in PP/DS
T13 | Load | Load stock balances | Inventory | Inventory lead | T06 |  | 3 | [5 empty] | Not started | Quantity and value reconciled with finance
T14 | Load | Load open purchase orders and open production orders | Data migration | Data lead | T11,T13 |  | 3 | [5 empty] | Not started | Counts reconcile with Open Order Strategy
T15 | Validation | Run MRP Live and PP/DS heuristics (where used) | Planning | PP lead | T12,T14 |  | 2 | [5 empty] | Not started | Planned orders reviewed with planners for key products
T16 | Validation | Smoke-test execution: convert, release, issue, confirm, receipt | Production | Production planner | T15 |  | 2 | [5 empty] | Not started | One end-to-end order completed
T17 | Decision | Go-live go/no-go decision | PMO | Steering committee | T16 |  | 0.5 | [5 empty] | Not started | Decision and sign-offs recorded
T18 | Go-live | Open system to users; start hypercare | PMO | Cutover lead | T17 |  | 0.5 | [5 empty] | Not started | Users notified; hypercare log active
Summary
| Tasks | 18
| Done | 0
| Blocked | 0
| % complete | 0%
| Planned hours | 38
Formulas:
Planned End = IF(OR([Planned Start]="",[Duration (hrs)]=""),"",[Planned Start]+[Duration (hrs)]/24)

## Open Order Strategy
Open Order Strategy
Decide per object how open documents are handled at cutover, then track counts against the decision.
Yellow cells are inputs. White cells with black text are formulas — don't overwrite them.
Object / document | Selection criteria (legacy) | Strategy | Rationale | Owner | Legacy cut-off (date) | Legacy open count | Target count in S/4HANA | Actual count in S/4HANA | Variance | Status | Notes
Planned orders | All open | Regenerate | Planning run in S/4HANA recreates them from demand and stock | [7 empty] | Example row — decisions must be agreed with planning and finance
Production / process orders — not started | Created, not released | Migrate
Production orders — in process | Released, partially confirmed | Close
Purchase requisitions | Open, not converted
Purchase orders / schedule lines | Open quantity > 0
Scheduling agreements | Valid at cut-off
Sales orders / customer demand | Open quantity > 0
Planned independent requirements | Future periods

## Load & Reconciliation
Load Sequence & Reconciliation
Load in dependency order. A row passes when both count and value variances are within tolerance.
Yellow cells are inputs. White cells with black text are formulas — don't overwrite them.
Seq | Object | Depends on (Seq) | Load method / tool | Legacy count | S/4HANA count | Count variance | Count var. % | Legacy value | S/4HANA value | Value variance | Tolerance % | Within tolerance? | Signed off by | Sign-off date | Notes
1 | Business partners (suppliers / customers) | [9 empty] | 0% |  |  |  | Tolerance 0% = exact match required; stock value row allows 0.1% for rounding (adjust with finance)
2 | Material master — basic data | 1 | [8 empty] | 0%
3 | Material master — plant / MRP views | 2 | [8 empty] | 0%
4 | Bills of material | 3 | [8 empty] | 0%
5 | Work centres / resources | 1 | [8 empty] | 0%
6 | Routings | 3,5 | [8 empty] | 0%
7 | Production versions | 4,6 | [8 empty] | 0%
8 | Planning data / PDS (if PP/DS) | 7 | [8 empty] | 0%
9 | Purchasing info records & source lists | 1,3 | [8 empty] | 0%
10 | Stock balances | 3 | [8 empty] | 0.1%
11 | Open purchase orders | 9 | [8 empty] | 0%
12 | Open production orders | 7,10 | [8 empty] | 0%
| Objects reconciled within tolerance |  |  | 0 of 12

## Go-No-Go
Go / No-Go Criteria
Agree criteria and thresholds before the first mock cutover. Overall result is GO only when every mandatory criterion is met.
Yellow cells are inputs. White cells with black text are formulas — don't overwrite them.
# | Category | Criterion | Threshold / evidence required | Mandatory? | Actual / evidence | Met? | Owner | Notes
1 | Data | Master data loaded and reconciled within tolerance | All rows 'Yes' on Load & Reconciliation | Yes
2 | Data | Stock balances reconciled with finance | Quantity and value sign-off | Yes
3 | Data | Open orders reconciled to the agreed strategy | Zero unexplained variance | Yes
4 | Testing | Critical defects closed | No open priority 1 / 2 defects | Yes
5 | Testing | End-to-end smoke test passed | Plan → produce → receive completed | Yes
6 | Planning | Planning run results reviewed with planners | Key products and bottleneck resources accepted | Yes
7 | People | Planners and key users trained | Training completion recorded | Yes
8 | Support | Hypercare team and issue process in place | Rota, contacts and log ready | Yes
9 | Business | Production plan for go-live week agreed | Build-ahead and contingency confirmed | Yes
10 | Rollback | Fallback plan understood | Decision point and steps documented | Yes
| Mandatory criteria | 10
| Mandatory criteria met | 0
| Overall decision | NO-GO

## Hypercare Log
Hypercare Issue Log
Log every issue after go-live. Days open counts to today until a resolved date is entered.
Yellow cells are inputs. White cells with black text are formulas — don't overwrite them.
ID | Date raised | Raised by | Area | Description | Priority | Owner | Status | Target date | Resolved date | Days open | Root cause / resolution
H001 | 2026-11-09 | Planner — Plant 1000 | Planning | Example: planned orders created with unexpected dates for one product family | P2 | PP lead | In progress | 2026-11-10 |  | 0 | Example row — replace or delete
|  |  | Open (not Resolved/Closed) | 1
|  |  | Open P1 | 0
|  |  | Open P2 | 1
Formulas:
Days open = IF([Date raised]="","",MAX(0,IF([Resolved date]="",TODAY(),[Resolved date])-[Date raised]))